Environmental Programs 2011 Outcomes

South West Campus Bushland (previously biodiversity)

Program Owner: 	Vice-President (Resources) & CFO

Program Manager:	Brian Yearwood

Steering Committee Member: 	Belinda O’Brien

Objective:

To manage the South-West Campus Bushland

Target:

- No loss of conservation significant flora species on the South-West Campus

- No loss of conservation significant fauna species on the South-West Campus

- Maintaining certification of ISO/ANZS 14001, Environmental Management Systems

Actions:-

- All developments on the South-West Campus that require clearing will be assessed against legal environmental requirements and appropriate action undertaken;

- Maintain a database of significant flora and fauna on the South-West Campus Bushland;

- Continued action to stop illegal vehicle access and illegal dumping of rubbish on the South-west Campus Bushland;

- Undertake a cool burn in an indentified high fire risk area by September 2011;

- Ongoing weed management including the removal of Flinders Range wattles;

- Plan and carry out an on-site seed collection activity with staff and students and set up a system for storing seeds from the bushland for future revegetation projects;

- Undertake an internal assurance review of the South-West Campus Bushland  Program by July 2011; and

- Undertake a certification audit of ECU’s ISO/ANZS 14001, Environmental Management Systems by November 2011.

Energy Consumption and Production

Program Owner: 	Vice-President (Resources) & CFO

Program Manager:	Brian Yearwood

Steering Committee Member: 	Belinda O’Brien

Objective:

To reduce energy use and carbon emissions associated with the Universities energy related operations

Targets:

- Reduce carbon emissions from (2008 carbon footprint inventory) electricity by 10% by 2020

- Remain in the top quartile of TEFMA benchmarking each year for Carbon Emissions (EFTSL+FTE) for Australian Higher Education Providers

- Maintaining certification of ISO/ANZS 14001, Environmental Management Systems

Actions:-

- Implement a number of carbon avoidance strategies including:-

- review of lighting on replacement;

- air-conditioning to reset once temperature drops below 20°C or increases above 25°C;

- develop a workplace inspection checklist to reduce carbon for Faculties and Centres and Green Office Representatives by March 2011;

- develop an environmental checklist check list for development projects by March 2011;

- develop an energy dash board by November 2011;

- install electricity meters for selected high use buildings;

- undertake a green IT project during 2011; and

- complete the 2010 carbon footprint inventory by August 2011.

- Complete a feasibility assessment for the implementation of a district energy scheme for the Joondalup Campus by June 2011;

- Continue implementation of ongoing electricity reduction projects through the Energy Management Group;

- Undertake an internal assurance review of the Energy Consumption and Production program by July 2011; and

- Undertake a certification audit of ECU’s ISO/ANZS 14001, Environmental Management Systems requirements by November 2011.

Water Consumption

Program Owner: 	Vice-President (Resources) & CFO

Program Manager:	Director Facilities and Services

Steering Committee Member: 	Belinda O’Brien

Objective:

To achieve continuous improvement and innovation in water conservation and water efficiency

Targets:

- Water consumption on each campus is reduced by 5% per annum on the 2008 TEFMA baseline per EFTSL

- Total water consumption remains below the 2008 TEFMA baseline per campus

- Maintaining certification of ISO/ANZS 14001, Environmental Management Systems

Actions:-

- Complete a feasibility study into the use and benefit of grey water and water harvesting recycling systems by October 2011;

- Retrofit 15 additional waterless urinals  by November 2011;

- Implementing a workplace inspection checklist to reduce water usage for Faculties and Centres and Green Office Representatives by March 2011;

- Complete a water audit for JO Building 21 by April 2011;

- Continue implementation of ongoing water reduction projects through the Water Management Group;

- Undertake an internal assurance review of the Water Consumption program by July 2011; and

- Undertake a certification audit of ECU’s ISO/ANZS 14001, Environmental Management Systems requirements by November 2011.

Travel

Program Owner: 	Vice-President (Resources) & CFO

Program Manager:	Brian Yearwood

Steering Committee Member: 	Trena Ward

Objectives:

- To reduce greenhouse gas emissions resulting from commute trips to/from ECU

- To reduce greenhouse gas emissions from staff use of the University fleet

Targets:

- The proportion of staff and students who commute to ECU using alternative forms of transport (e.g. non-motorised personal vehicles) to be 10% higher than the 2010 baseline (Travel Survey) by 2020

- Greenhouse gas emissions from the University Fleet reduced by 10% of the 2008 baseline by 2020

- Maintaining certification of ISO/ANZS 14001, Environmental Management Systems

Actions:-

- Continue to provide information to staff and students on public transport available;

- Re-market the car pooling system by June 2011;

- Develop an ECU Campus Access Strategy by November 2011;

- Faculties and Centres to provide access to smart rider cards for staff to increase the use of public transport for work related travel by June 2011;

- Undertake an event at each campus as part of Bike Week in March 2011;

- Undertake a travel survey in 2012;

- Provide information on carbon resulting from air travel for each Faculty and Centre by September 2011;

- Undertake an internal assurance review of the Travel program by July 2011; and

- Undertake a certification audit of ECU’s ISO/ANZS 14001, Environmental Management Systems requirements by November 2011.

Waste Produced

Program Owner: 	Vice-President (Resources) & CFO

Program Manager:	Brian Yearwood

Steering Committee Member: 	Trena Ward

Objectives:

Reduce waste to landfill as a result of activities under the control of Facilities and Services

Targets:

- Reduce waste to landfill by 20% from 2008 benchmark by 2015

- Maintaining certification of ISO/ANZS 14001, Environmental Management Systems

Actions:-

- Develop two education projects in 2011 to increase the use of recycling bins and recycling processes across the University by December 2011;

- Implement a new cleaning and waste contract with improved measurement of waste produced by the University by July 2011;

- Review the KPIs for the Waste Produced Program following the implementation of the Cleaning and Waste Contract and by November 2011;

- Implement recommendations from a review of e-waste collections following the 2010 e-waste collection review by March 2011;

- Implement improved waste recycling processes for building projects by September 2011;

- Implement a workplace inspection checklist to reduce waste to landfill for Faculties and Centres and Green Office Representatives by March 2011;

- Roll out the mini bin and paper box system to two buildings on each campus by November 2011;

- Establish recycle bins in commercial outlets by July 2011;

- Undertake an internal assurance review of the Waste Produced program by July 2011; and

- Undertaking a certification audit of ECU’s ISO/ANZS 14001, Environmental Management Systems requirements by November 201.